## Master
Topic | Task | Status | Start Date | End Date | Assigned to | Support | Budget Notes | Comments
Project Management
Complete project charter/business case
Establish project team / resources and PM/CM approach
Complete workplan (PM/CM)
Communicate charter/workplan to internal FCO and External Centre project team
Initiation
FCO and site leadership call - site award notification
Orientation
#1 orientation session with FCO, Lead Agency and Key Partners
#2 Kick-off meeting with partners #2 Orientation
#3 Orientation Community cont'd as appropriate
Establish funders table
Establish leadership table
Establish Operations Working Group
Establish youth advisory group
Establish family advisory group
Establish TOR for all working groups
Contract execution (LOI, Capital Contract, ISA, HA service contract, MOU, etc., )
Partnership Engagement
ID & develop partnership engagement and analysis
ID & develop youth engagement strategy
ID champion (leadership capacity to lead youth engagement)
ID & develop family engagement strategy
ID champion (leadership capacity to lead family peer support & family engagement)
Change Leadership
Develop Foundry Centre specific story to coincide with the Foundry story (Vision & Awareness & Desire)
Orientation - Change Leadership - Sponsor - what it means to be an active/visible sponsor
Capital Project | Perform commercial real-estate scan
Identify physical location
Review foundry space planning guide
Develop functional program- capital
Perform post occupancy evaluation
Communications | Orientation to the brand (branding process, DNA, etc.)
Develop communications plan
Develop announcement plan and event strategy with LA and Ministry
Budgets/Contracts | Budget/Contracts
Capital budget
Contract execution (LOI, Capital Contract, ISA, HA service contract, MOU, etc., )
Fundraising | Fundraising
ID fundraising partners and develop plan
Fundraising capacity assessment
Confirm philanthropic dollars
Close out fundraising campaign, announce results
Support LA to finalize donor wall, as needed
Center Operations Governance Development
Centre Service Support Scan
ID which services Lead Agency
ID services available in the community that support Foundry model
Solicit in-kind resources to support delivery of services at Foundry Centre
Develop strategic partnership to compliment existing agency services and fill gaps
MOU (renew)
Educate partners on the Foundry Service Model including ISCM as the core framework of service partnership development
Foundry Support Planning
Determine if partners can contribute to:
Operational Partnership Development | Software lease costs
Lease costs & shared services
Shared administrative staff
Tool - Service scan
Orientation to KE for Operations managers and training plan (high level)
Foundry, ISCM and walk-in services
Develop infrastructure for WIC
Develop infrastructure for ISCM
Create an organizational chart and identify reporting structure
Policy and procedure development
Review existing policies and procedures
Establish shared agreements on for service delivery commitments
IT requirements
Operations Planning | Assess partner functional requirements to operate on site
Partner commitment to use Toolbox
Ensure Toolbox IT requirements accommodated
Communication
Team meetings
Internal Referrals
External Referrals
Orientation plan for frontline team members
Staffing infrastructure/model development
Physician Contracts in place
Service Planning | Client care planning
Service pathways and workflow development
Most Responsible Care Provider
Collaborative Care planning Rounds
Clinical protocols in place (crisis intervention)
Supervision model
Model of Care document completed
Standards orientation and implementation
Youth Peer Support
Family Peer Support
Walk in Counselling
Standards for ISCM Pathways
Mood, anxiety, distress
Substance use
Psychosis
Disorder eating
Service pathways and workflow - Mental Health
Screening/ Assessment
Walk In counseling
Individual Therapy
Groups
Family support
Outreach
Psychiatry
Service pathways and workflow - Substance Use
Screening/ Assessment
individual Therapy
Harm Reduction
Groups
Family Support
Service pathways and workflow - Primary Care
Transcare
Physical Health
Sexual Health
Addictions Medicine (OAT)
Shared Care
Service pathways and workflow - Peer Support
Service pathways and workflow - Social Services
Housing
Vocation
STADD
Income assistance
Cultural Services
Training
Toolbox
EFFT
SFBT walk-in counselling
Youth Peer Support
Family Peer Support
Cultural Safety (for all)
Family Support (for all)
Team Development | Integration with intention
Develop a team agreement that supports a culture of integration
Schedule annual team retreat
Sustainment and evaluation plan | Orientation to evaluation/performance measurement strategy (including Toolbox)
Toolbox implementation
Survey administration (youth, family/caregiver, staff, partners)
Tracking turnaways & Waittimes
Follow-up to address issues (data quality follow up)
Data feedback (at least monthly) and analysis
Making requests for site specific data
Special Project | Virtual Care
ISCM
PCN
School District
Diversity working group led by FCO
Mobile
Wellness Project
FOUNDRY Workplan - Master Plan On-boarding and Operations
Department/Project